90-Day Plan

Head of AI & Automation — Execution Plan

Fintech  •  Microsoft + AI Foundry  •  Africa

Version 1.0  •  Classification: Internal

# Executive Summary

This plan sets out what the Head of AI & Automation will deliver in the first 90 days in role. It is written to be testable: every commitment has an owner, a date, and a visible output. It is deliberately conservative on scope and ambitious on posture — we will establish the operating model, make the enterprise AI footprint visible and controlled, land two high-signal value proofs, and leave the organisation with a repeatable intake-to-production path.

Three conditions frame the plan. First, Microsoft 365 Copilot has already been deployed enterprise-wide — so this is not a greenfield rollout; it is a posture-and-controls audit plus an expansion and optimisation programme. Second, the approved stack is Microsoft + Azure AI Foundry, which simplifies architecture decisions and compresses vendor onboarding. Third, we operate in a regulated fintech context across multiple African jurisdictions, so every move must be defensible to SARB, CBN and equivalent supervisors and to our Data Protection Officers under POPIA, NDPA and KDPA.

## Headline commitments

- Day 30 — Operating model stood up: AI Council chartered, framework v1.0 issued, use-case register live, M365 Copilot controls audit complete with remediation plan.

- Day 60 — Two value proofs in flight: one Tier-2 copilot in a high-volume operational domain; one developer-productivity proof comparing GitHub Copilot Enterprise vs. Claude Code on Foundry against the same baseline.

- Day 90 — Portfolio and scale: 2–3 use cases in production or pilot, first quarterly Board Risk Committee update delivered, 12-month roadmap and investment case signed off.

# Guiding Principles for the 90 Days

- Move at the speed of trust. Spend the first two weeks listening — to regulators, risk, engineering, the business and the DPO — before issuing anything.

- Make the invisible visible. The biggest risk is AI that is already running without controls. We discover and register before we approve more.

- Prefer small reversible bets. Choose use cases where failure is cheap, success is measurable, and we learn something either way.

- Governance and velocity are not opposites. A lightweight, enforced intake is faster than ungoverned sprawl, because it prevents rework and regulatory escalations.

- Two concrete wins beat one abstract strategy. By Day 90 leadership should be able to point to a running system the business actually uses.

# Day 1–30 — Listen, Make Visible, Anchor

The first 30 days focus on establishing ground truth and standing up the operating model. We do not approve net-new AI systems in this window unless they are already committed or there is a clear business-continuity reason.

## 1.1 Listening tour

Structured 1:1 and small-group meetings across stakeholder groups, with a written summary issued on Day 21.

| Stakeholder | Meeting purpose | Output |
| --- | --- | --- |
| CEO, CFO, COO | Confirm strategic priorities, risk appetite, and what a good Day-90 looks like. | Written alignment note. |
| CIO / CTO, Head of Engineering | Review current tooling, platform roadmap, delivery metrics, prior AI attempts. | Architecture debt list. |
| CISO, Head of IT Risk | Identity, data egress, DLP, threat model for AI; Sentinel coverage; red-team posture. | Control gap register. |
| CRO, Head of Model Risk, DPO | Model inventory, POPIA/NDPA/KDPA posture, model-risk framework status. | Risk and privacy baseline. |
| General Counsel, Compliance | Regulatory interpretation posture (SARB, CBN, CMA, BoG), AI disclosure requirements. | Legal horizon scan. |
| Business heads (Retail, Business, Ops, CX) | Pain points, candidate use cases, appetite for copilot adoption in their teams. | Ranked use-case long list. |
| Frontline — agents, relationship managers, dev leads | Where is time actually lost? What is already being used (licit or shadow)? | Shadow-AI inventory. |
| External — Microsoft, Big-4, peer CIOs | Reference architectures, peer benchmarks, Foundry roadmap, pricing leverage. | Vendor engagement plan. |

## 1.2 M365 Copilot controls audit (already-live footprint)

Because M365 Copilot has already been rolled out to all users, the single highest-value action in Week 1–2 is to audit the existing footprint and close any posture gaps before they surface under audit. This is the opposite of a rollout task — the tool is already in people's hands; we are verifying that the guardrails around it match the risk.

| Audit area | What we check | Owner |
| --- | --- | --- |
| Identity and licensing | All Copilot users are in Entra ID, MFA enforced, conditional access aligned, break-glass accounts separated, service-principal use reviewed. | IAM lead |
| Data boundary | Confirm tenant data is not used to train Microsoft's foundation models. Verify EU / regional data residency settings and in-geo processing commitments. | DPO |
| Sensitivity labels (Purview) | Confidential and Restricted labels enforced; label-inheritance on Copilot outputs; blocked access to unlabelled high-risk SharePoint sites. | Information Protection |
| Oversharing and access review | SharePoint / OneDrive oversharing scan; Copilot access reviews on sites with customer PII; legacy 'Everyone except external users' groups removed or restricted. | SharePoint admin |
| DLP and prompt protection | Purview DLP policies cover Copilot prompts and responses; high-risk data patterns (card data, ID numbers) blocked or warned. | CISO office |
| Audit and eDiscovery | Copilot interactions flow into Purview Audit and are discoverable for regulatory and HR matters; retention policies aligned. | Compliance |
| Usage analytics | Copilot Dashboard baseline: adoption, active users, top use patterns; cost-per-active-user; identify dormant licences for reallocation. | AI & Automation |
| User readiness | Verify Acceptable Use training completion, sample prompt-and-response review on low-risk content, feedback channel active. | HR / L&D |
| Incident readiness | Playbook exists for a Copilot-surfaced data leak; integrated with Sentinel and the AI incident process in the Governance Framework §11. | SOC |

Output: a signed M365 Copilot Controls Audit report by Day 25 with a remediation plan. Any Red findings are assigned to a named owner with a fix-by date, and the largest three are reported in the Day-30 status update.

## 1.3 Stand up the operating model

- Issue the AI Governance Framework v1.0 (this package) and socialise with ExCo, CISO, CRO, DPO, GC.

- Charter the AI Council. Confirm permanent members (see Framework §4.1), set first meeting in Week 3, issue monthly cadence.

- Stand up the AI Use-Case Register (SharePoint list backed by Purview; or Dataverse if Copilot Studio governance is adopted).

- Publish the Use-Case Intake Form (Framework Appendix A) and open the intake inbox.

- Confirm Acceptable Use Policy (Framework §10) is communicated and attested by all users via HR system; target 100% attestation by Day 30.

- Run an immediate shadow-AI amnesty: 14-day window where teams self-declare AI tools already in use without penalty. Register everything declared.

## 1.4 Initial AI Foundry foundation (thin)

The goal is a thin, defensible platform — not a full build-out. Details live in the Sandbox Reference Architecture document. Day 30 target is an empty-but-secure landing zone, not a populated platform.

- Azure landing zone for AI: dedicated subscriptions for Dev, Non-Prod, Prod; Azure Policy initiative applied; private networking baselined.

- One Foundry hub + one Dev project stood up; Entra groups wired; Key Vault, Log Analytics, Defender for Cloud enabled.

- Approved-model list registered: Azure OpenAI GPT-4.1 / GPT-5 class, Claude Sonnet 4.6 and Haiku 4.5 on Foundry (Opus 4.7 pending cost-control sign-off), embedding models.

- Baseline evaluations, content-safety filters, PII redaction and prompt-shield applied to the Dev project.

## 1.5 Day-30 exit criteria

| Commitment | Status gate |
| --- | --- |
| AI Governance Framework v1.0 issued and acknowledged by ExCo. | Signed |
| AI Council chartered with first meeting held and minutes issued. | First meeting held |
| Use-case intake open; register live with at least the M365 Copilot entry and Shadow-AI amnesty declarations. | ≥ 10 entries |
| M365 Copilot controls audit complete with remediation plan; top 3 Red findings have named owners and fix-by dates. | Report signed |
| Foundry Dev landing zone live with approved-model list and content safety. | Deployed |
| Acceptable Use attestation at ≥ 95% of active users. | 95%+ |
| Listening-tour summary circulated with ranked use-case long list (≥ 15 candidates). | Issued |

# Day 31–60 — Prove, Pilot, Pressure-Test

The second 30 days move from posture to evidence. Two value proofs are chosen from the use-case long list, one business-facing and one developer-facing, and run through the Framework's intake-to-pilot gates. A controls pressure-test (red team) is executed on the M365 Copilot posture from Day-30 remediation.

## 2.1 Use-case portfolio — selection criteria

We select from the long list produced in Day 1–30. The selection bar is written down so the choice is defensible to the Council and to the Board:

- High and measurable value (time saved, revenue captured, risk reduced) with a clear hypothesis.

- Tier 2 or below — no decisioning use cases in the first window; decisioning waits for full validation framework.

- Clean data environment — the data exists, is governed, and is already classified under Purview.

- Business sponsor with skin in the game — a named executive who will use the system and present the outcome at Day-90.

- Reversible — can be paused or withdrawn without material customer or financial impact.

## 2.2 Value proof 1 — operational copilot (business-facing)

Representative candidate (subject to Council confirmation): a copilot for Contact Centre or Client Services agents that retrieves relevant product, policy and account information and drafts responses. Deployed initially to a volunteer squad of 15–25 agents, with before/after measurement.

| Item | Commitment |
| --- | --- |
| Approach | Retrieval-Augmented Generation (RAG) over curated product and policy content; Azure OpenAI with content safety; Copilot Studio for the UX shell. |
| Tier | Tier 2 (advisory to agent; does not commit the bank; agent remains accountable). |
| Metrics | Average handle time, first-contact resolution, post-call survey score, policy-citation accuracy (human-audited weekly). |
| Guardrails | Response grounded in citations; refusal-to-answer on off-scope queries; red flags surfaced to supervisor; full audit log. |
| Exit criteria | Day-60: pilot live with ≥ 15 agents and baseline vs. pilot metrics captured weekly. Day-90: go/no-go decision with evidence pack. |

## 2.3 Value proof 2 — developer productivity bake-off

Run the parallel pilot defined in the GitHub Copilot Rollout Plan §2.1 and Appendix C: GitHub Copilot Enterprise vs. Claude Code on Foundry on the same baseline, with 12–15 engineers per track across comparable workloads. Both tools feed through the same DORA + quality metrics pipeline.

- Day 35 — pilot squads selected and baselined (two sprints of pre-pilot DORA data captured).

- Day 45 — both tracks live; weekly pulse check with squad leads.

- Day 55 — interim read-out to AI Council with initial metrics.

- Day 60 — pilot continues; decision point scheduled for Day 75–90.

## 2.4 Controls pressure-test (red team)

A targeted red-team exercise on the M365 Copilot posture and the new Foundry landing zone, scoped to verify that the Day-30 remediation actually holds up.

- Prompt-injection scenarios against a test M365 Copilot tenant using staged documents.

- Oversharing check: can a junior role surface confidential HR or finance content through Copilot that it should not see?

- Data-exfiltration scenarios against the Foundry Dev project — DLP coverage on egress, Key Vault access patterns, model-endpoint abuse.

- Output: red-team report with findings classified High / Medium / Low, remediation timelines, and re-test plan.

## 2.5 Governance discipline

- Second AI Council meeting held — approvals for the two value proofs recorded; shadow-AI amnesty cases dispositioned.

- Model / tool approval list updated (Framework §7) as needed; any new tools from the shadow-AI amnesty either approved, migrated to an approved equivalent, or blocked.

- First monthly AI metrics pack issued (Framework §13): portfolio posture, adoption, incidents, cost.

## 2.6 Day-60 exit criteria

| Commitment | Status gate |
| --- | --- |
| Operational copilot pilot live with ≥ 15 users and weekly metrics captured. | Live & measured |
| GitHub Copilot vs. Claude Code parallel pilot live with baselined squads. | Both tracks live |
| Red-team report issued; High findings closed or on a named remediation plan. | Signed |
| Shadow-AI amnesty cases closed — every item approved, replaced, or blocked. | All dispositioned |
| Second AI Council held; monthly AI metrics pack v1 issued. | Issued |

# Day 61–90 — Scale, Decide, Institutionalise

The last 30 days convert evidence into decisions. We run the formal go/no-go on the two proofs, ship the 12-month roadmap and investment case, and hold the first Board Risk Committee deep-review.

## 3.1 Go / no-go decisions

- Operational copilot: go-live decision to a larger squad (target 60–100 agents) if pilot metrics meet pre-agreed thresholds; otherwise iterate-or-retire with a written rationale.

- Developer tool bake-off: decide whether to scale on GitHub Copilot Enterprise alone, dual-track for specific workloads, or adopt Claude Code on Foundry for a specific engineer cohort. Decision documented with the full metrics pack.

## 3.2 12-month roadmap and investment case

A Now / Next / Later view covering the next four quarters, with a bounded investment case (see the Business Case & Budget document for details). It should include:

- Portfolio: 6–10 named use cases with tier, sponsor, stage, expected value and investment.

- Platform: Foundry maturity curve (Dev → Prod), Copilot Studio governance, agent framework, evaluation pipeline.

- People: hiring plan for the AI & Automation function (see §3.4).

- Financials: run-rate by cost category, sensitivity scenarios, benefits realisation curve.

## 3.3 Board Risk Committee deep-review

First quarterly deep-review pack, covering:

- Portfolio snapshot — tiers, pilots, production, incidents.

- M365 Copilot posture — audit outcomes, remediation progress, red-team results.

- Regulatory horizon — POPIA / NDPA / KDPA; SARB / CBN / CMA / BoG positioning; EU AI Act relevance; ISO 42001 gap.

- Ask — investment case, hiring plan, cross-functional commitments needed.

## 3.4 People and partners

- AI & Automation function target shape: Head; AI Platform Engineer; ML / MLOps Engineer; AI Governance Lead; AI Product Manager; solutions partners x2 (Council on secondment).

- Confirm first two hires or internal moves — typically AI Governance Lead and AI Platform Engineer as they unblock everything else.

- Microsoft co-sell / AI Design Win engagement confirmed and Microsoft funding / credits secured where available.

- Partner bench: 1–2 implementation partners for surge capacity; 1 independent validator for Tier-1 model review.

## 3.5 Day-90 exit criteria

| Commitment | Status gate |
| --- | --- |
| Operational copilot go/no-go decision made with evidence; scale decision documented. | Decided |
| Developer tool bake-off decision documented and communicated. | Decided |
| 12-month roadmap and investment case approved by ExCo. | Signed |
| Board Risk Committee deep-review held with written pack tabled. | Held |
| First two hires / internal moves into AI & Automation function confirmed. | Offers out |
| Portfolio: 2–3 use cases in pilot or production; ≥ 15 in the register. | Live |

# Governance of the Plan Itself

- Weekly status update to the CIO/CTO; monthly status to ExCo; quarterly to Board Risk Committee.

- Plan on-a-page tracked in a single dashboard — green / amber / red by workstream — reviewed every Monday.

- Variance from plan is flagged early with a named cause and a proposed adjustment; plans do not silently slip.

- Every deliverable lands with a written artefact stored in the AI & Automation SharePoint site, not just a verbal update.

# Key Risks and Mitigations

| Risk | Likelihood × Impact | Mitigation |
| --- | --- | --- |
| M365 Copilot oversharing leaks confidential content before audit lands | M × H | Day-1 priority audit; temporary Purview label restrictions on highest-risk sites; SOC on heightened monitoring until Day 25. |
| Shadow-AI tools continue after amnesty window | H × M | Post-amnesty, egress DLP blocks unapproved AI endpoints; HR policy updates make unregistered use a disciplinary matter. |
| Council captured by loudest voices, fast-track used to bypass controls | M × M | Tier criteria (Framework §5) documented and audited; Chair logs every Tier-reduction with rationale; quarterly independent review. |
| Pilot success → scope creep; teams launch before validation | M × H | Framework §6 stages are gates, not stages; acceptance letter is a hard control; DevOps pipelines block unregistered models from Prod. |
| Hiring / partner capacity slips; plan stalls at Day 45 | M × M | Backfill from partner bench for up to 90 days; prioritise AI Governance Lead hire; CIO loan-out engineer for Foundry platform work. |
| Regulator raises AI concerns mid-cycle (SARB / CBN / DPO) | L × H | Governance Framework written pre-emptively to meet the bar; proactive DPO and compliance engagement; ability to pause specific use cases within 24 hours. |

# Dependencies and Asks

- ExCo — endorsement of the AI Governance Framework and the AI Council charter within two weeks of issue.

- CIO / CTO — platform engineering capacity for Foundry landing zone (two engineers, part-time, for 30 days).

- CISO — red-team time-box (1 week) in Day 45–55 and integration of Copilot events into Sentinel.

- CRO / DPO — co-authorship of use-case assessment templates and sign-off on data boundary posture by Day 20.

- HR / L&D — Acceptable Use attestation campaign in first 2 weeks and role-level AI training path within 60 days.

- Finance — budget envelope for platform and pilots under existing Azure commit, plus ring-fenced T&M for pilot measurement (see Business Case document).

- Microsoft — accelerated access to Foundry features (Claude models, agent frameworks), design-win funding, Purview tuning support.

# Communications Plan

| Audience | Channel & cadence | Content |
| --- | --- | --- |
| ExCo | Monthly written update + standing agenda slot | Plan progress, risks, decisions needed, material incidents. |
| Board Risk Committee | Quarterly deep-review | Portfolio posture, material changes, regulatory horizon, hiring. |
| AI Council | Monthly standing; ad-hoc for incidents | Approvals, portfolio, incident log, policy changes. |
| All staff | Monthly digest + intranet hub | What's approved, how to propose a use case, wins and lessons. |
| Engineering | Bi-weekly community of practice | Copilot tips, pilot telemetry, architecture patterns, office hours. |
| Regulators / DPO | On-request + scheduled briefings | Framework pack, incident summaries, portfolio under supervision. |

# Appendix A: Week-by-Week Snapshot

A condensed view for the programme dashboard. Owners are named on the live plan.

| Week | Primary focus | Key outputs |
| --- | --- | --- |
| W1 | Listen, triage, audit kick-off | Stakeholder schedule locked; M365 Copilot audit launched; AI Council charter circulated. |
| W2 | Shadow-AI amnesty; Foundry baseline | Amnesty window opened; Foundry landing zone design approved; AUP attestation campaign started. |
| W3 | Operating model live | First AI Council meeting; intake register open; framework v1.0 issued. |
| W4 | Close listening; finalise audit | Listening-tour summary; M365 Copilot audit signed; Foundry Dev live. |
| W5 | Select value proofs | Use-case selection presented to Council; pilot squads identified. |
| W6 | Baseline metrics | DORA + quality baseline captured; operational copilot data loaded; pilot plans signed. |
| W7 | Pilots live | Operational copilot in the hands of first agents; dev bake-off starts. |
| W8 | Red team | Red-team exercise run; findings triaged. |
| W9 | Interim read-out | Second Council; monthly metrics pack v1; red-team remediation on track. |
| W10 | Roadmap draft | Now/Next/Later roadmap draft; investment case draft; hiring plan drafted. |
| W11 | Go / no-go prep | Evidence packs finalised; ExCo pre-read issued; hiring interviews underway. |
| W12 | Decisions, Board review | Go/no-go decisions taken; roadmap approved; BRC deep-review held. |