INTELLIGENT TEST AUTOMATION

Strategy & Execution Plan

MTN Group Fintech

AI & Automation Division

Document Owner: Malcolm Govender, Head of AI & Automation

Version 1.0 · April 2026

Classification: Internal — Technology Division

# 1. Executive Summary

MTN Group Fintech runs release cycles across 17 markets supporting 290M+ customers. Quality assurance is currently squad-embedded, manual-heavy, and uneven in coverage. This strategy establishes an AI-driven test automation capability that will lift regression coverage by 3×, reduce release cycle time by 35%, and cut production defect escape rates by half within 12 months.

The approach is pragmatic: start with two pilot squads, prove measurable value in 90 days, then scale across engineering. We build on commercial LLMs for test generation, open-source frameworks for execution, and lightweight ML for defect-risk prediction — no vendor lock-in, no moonshot bets.

Headline targets (12 months):

- Regression coverage: baseline → 3× across pilot squads

- Release cycle time: −35%

- Production defect escape rate: −50%

- Flaky test rate: −60%

- Engineer hours reclaimed from manual test maintenance: ~25% per pilot squad

# 2. Problem Statement

Across MTN Fintech engineering, testing is the primary bottleneck slowing release confidence. The pattern is consistent across squads:

- Regression suites grow faster than they are maintained — flakiness compounds, teams disable failing tests rather than fix them

- Test generation is still manual and driven by developer discretion, leading to uneven coverage of edge cases and non-happy-path flows

- Defect prediction is reactive — issues are discovered in staging or production rather than prevented at PR time

- Cross-squad test patterns and fixtures are not shared, each squad reinvents its tooling

- QA engineers spend an outsized share of their time on maintenance rather than strategic coverage design

The cost of this is not primarily test infrastructure — it is slower releases, deferred feature work, and a compliance tax every time a significant MoMo change ships.

# 3. Strategic Objectives

## 3.1 Primary Objectives

- Establish an AI-assisted test automation capability as a division-wide shared service within 6 months

- Prove measurable release confidence uplift in two pilot squads within 90 days of capability launch

- Scale to five additional squads by end of Q4 2026 with self-service tooling and playbooks

- Publish internal standards for AI-generated test code review, security, and maintainability

## 3.2 Secondary Objectives

- Feed anonymised test outcomes into the broader AI platform to improve defect prediction over time

- Reduce the total QA headcount pressure per squad by shifting maintenance load to the shared service

- Create a defensible capability the Group Risk & Compliance function can audit for regulated releases

# 4. Scope

## 4.1 In Scope

- Unit, integration, API, and end-to-end UI test generation and maintenance

- CI/CD pipeline integration at the PR and merge-to-main stages

- Defect-risk scoring on PRs (recommend reviewers, flag high-risk changes)

- Self-healing selectors for UI tests

- Flaky test detection and auto-quarantine

- Test data management for pilot squads

## 4.2 Out of Scope (Phase 1)

- Performance and load testing (deferred to Phase 2)

- Security penetration testing (handled by Security Testing function)

- Mobile device farm management (separate investment)

- Manual exploratory testing — remains a human-led activity and will not be replaced

# 5. Technical Approach

## 5.1 Capability Stack

| Layer | Purpose | Tooling |
| --- | --- | --- |
| Generation | AI-driven creation of tests from requirements and code diffs | Claude Sonnet via Agent SDK |
| Execution | Cross-language test runners with parallel execution | Playwright, pytest, Jest |
| Orchestration | Pipeline integration, parallelisation, reporting | GitHub Actions, Argo Workflows |
| Intelligence | Defect prediction, flaky detection, coverage analysis | Python + scikit-learn, OpenTelemetry |
| Governance | Audit logging, HITL review gates, traceability | Langfuse, internal policy engine |

## 5.2 Build vs. Buy

The vendor scan (Diffblue, Mabl, CodiumAI, Testim) shows strong point solutions but none cover the full pipeline we need at MTN's scale and compliance bar. The decision is to build a thin internal layer on commercial LLMs and open-source execution frameworks, avoiding lock-in and preserving the ability to switch model providers.

## 5.3 Human-in-the-Loop Design

All AI-generated test code lands as a PR authored by the test-generation agent. A human engineer reviews and approves before merge. The agent does not merge its own code. This is deliberate — we are augmenting engineering judgement, not replacing it.

# 6. Execution Plan

| Phase | Weeks | Focus | Exit Criteria |
| --- | --- | --- | --- |
| Discovery | 1–3 | QA estate survey, pilot squad selection, success metrics baseline | Signed pilot charter with 2 squads; baselined coverage, flakiness, cycle time |
| Foundation | 4–7 | Agent scaffold, Playwright integration, PR workflow, Langfuse tracing | Working end-to-end: story → generated tests → PR → review → merge |
| Pilot | 8–16 | Run both pilot squads on the capability, iterate weekly | Measurable uplift on all 5 headline metrics; pilot squads retain the capability |
| Scale | 17–26 | Onboard 5 further squads, publish playbooks, graduate to shared service | 5 additional squads using the capability; self-service onboarding documented |
| Phase 2 | 27+ | Performance testing, mobile device farm integration, defect-risk at scale | Capability extended to new domains |

# 7. Success Metrics

All metrics are baselined at the start of pilot and reviewed weekly during pilot phase, monthly once scaled.

| Metric | Baseline | 90-Day Target | 12-Month Target |
| --- | --- | --- | --- |
| Regression coverage | TBD per squad | +50% | 3× baseline |
| Release cycle time | TBD per squad | −15% | −35% |
| Production defect escape rate | TBD per squad | −20% | −50% |
| Flaky test rate | TBD per squad | −30% | −60% |
| Engineer hours on maintenance | TBD per squad | −10% | −25% |
| AI-generated test acceptance rate | N/A | >50% of suggestions | >75% of suggestions |

# 8. Risks & Mitigations

| Risk | Likelihood / Impact | Mitigation |
| --- | --- | --- |
| AI-generated tests are low quality and require heavy rework | Medium / High | Hard HITL gate; track acceptance rate weekly; kill switch if <30% |
| Squads reject the capability as top-down imposition | Medium / High | Pilot squads selected with their opt-in; capability ships as optional |
| API cost overruns from aggressive test generation | Medium / Medium | Budget cap per squad per month; monitor token usage via Langfuse |
| Flaky test problem worsens as volume grows | High / Medium | Auto-quarantine flaky tests; weekly flake review; SLO on flake rate |
| Compliance concern over AI-generated code in regulated markets | Medium / High | Early engagement with Group Risk; full audit trail via Langfuse; human sign-off required |
| No dedicated QA Automation Lead hired in time | High / High | Open role now; interim leadership by Head of AI & Automation |

# 9. Team & Governance

## 9.1 Core Team (Target)

- QA Automation Lead (1 FTE) — owns the capability end-to-end

- AI/Automation Engineer (1 FTE) — agent development and prompt engineering

- Data Scientist (0.5 FTE) — defect risk model, flaky detection

- Platform Engineer (0.5 FTE) — CI/CD integration, infra

## 9.2 Governance Model

- Weekly Pilot Review — squads, QA Lead, Head of AI & Automation

- Monthly Steering — Head of Engineering, Head of QA (if separate), Head of AI & Automation, Risk representative

- Quarterly Board Update — included in AI & Automation division report

# 10. Dependencies

- Hiring: QA Automation Lead open now, target start within 8 weeks

- Infrastructure: GPU/compute budget for model calls signed off

- Data Access: read access to historical CI/CD run data for defect-risk model

- Security: Security review of Claude API data handling, completed before pilot starts

- Sponsor Alignment: Head of Engineering commits 2 pilot squads for 12-week pilot window

# 11. Appendix — References

- Multi-Agent Stack Briefing (Malcolm Govender, April 2026) — foundation platform this strategy builds on

- MoMo Intelligence Centre — live dashboard for AI & Automation programme status

- MTN Head of AI & Automation JD — scope of the broader division

- Vendor scan notes — Diffblue, Mabl, CodiumAI, Testim comparison (internal Notion)